## ECS Go Live Plan
SR | Task Name | Start Date | End Date | Resource Name | Comments
1 | Program Governance & Steering | 2026-07-01 | 2026-12-31 | Project Manager | Overall ECS delivery, CIO reporting
2 | Phase-1 App Onboarding (Mobile Banking) | 2026-07-01 | 2026-08-15 | Integration Engineer 1 | Pilot application
3 | Phase-1 App Onboarding (Net Banking) | 2026-07-01 | 2026-08-15 | Integration Engineer 2 | Pilot application
4 | Phase-1 App Onboarding (Payments) | 2026-08-01 | 2026-09-15 | Integration Engineer 1 | Pilot application
5 | Phase-1 App Onboarding (UPI) | 2026-08-01 | 2026-09-15 | Integration Engineer 2 | Pilot application
6 | Metadata Tagging AI Use Case | 2026-07-01 | 2026-08-31 | AI Engineer 1 | MD use case from uploaded workbook
7 | Evidence Querying AI Use Case | 2026-07-01 | 2026-09-30 | AI Engineer 2 | MD use case from uploaded workbook
8 | Completeness Detection | 2026-08-01 | 2026-10-15 | AI Engineer 1 | MD use case from uploaded workbook
9 | Evidence Summaries | 2026-08-01 | 2026-10-31 | AI Engineer 2 | MD use case from uploaded workbook
10 | Audit Queries | 2026-09-01 | 2026-11-30 | AI Engineer 1 | MD use case from uploaded workbook
11 | CI/CD & Release Automation | 2026-07-01 | 2026-12-31 | DevOps Engineer 1 | Production pipelines
12 | Kubernetes & Secrets | 2026-07-01 | 2026-12-31 | DevOps Engineer 2 | Platform operations
13 | Monitoring & Observability | 2026-07-01 | 2026-12-31 | SRE Engineer 1 | SLA/SLO dashboards
14 | Performance & Capacity | 2026-07-15 | 2026-12-31 | SRE Engineer 2 | Production readiness
15 | Evidence Repository DB | 2026-07-01 | 2026-09-30 | Database Engineer 1 | Postgres and retention
16 | Analytics & Reporting DB | 2026-08-01 | 2026-12-31 | Database Engineer 2 | Executive dashboards
17 | Executive Dashboard Development | 2026-07-15 | 2026-10-31 | Software Engineer 1 | ROI, CIO, Audit views
18 | Framework Automation Services | 2026-07-15 | 2026-11-30 | Software Engineer 2 | VAPT, PCI DSS, DPSC etc
19 | Scale from 4 to 25 Applications | 2026-10-01 | 2026-12-31 | All Teams | Enterprise rollout

## MD Use Cases
Use Case | Phase
Metadata tagging | Covered
Evidence querying | Covered
Completeness detection | Covered
Evidence summaries | Covered
Audit queries | Covered